## Template
Lofthus Frukt og Saft Website |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
Start date: 18.11.2019 | End date: 13.12.2019 |  | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
Planning |  | 3d
Contact with Team and Stakeholders | Project Manager | 20d
Initial meeting and requirement gathering | Whole Team with stakeholders | 1d | bar: WEEK 1 M
Functional Specification | Whole Team | 1d | bar: WEEK 1 T
Gantt Chart and approval | Project Manager | 1d | bar: WEEK 1 W
Design |  | 7d
Wireframes | UX Designer | 3d | bar: WEEK 1 TH to WEEK 2 M
Styletile | Front-end Developer | 3 d | bar: WEEK 1 TH to WEEK 2 M
Photography and editing | Photographer | 7d | bar: WEEK 1 TH to WEEK 2 TH
Collecting and writing text | Copywriter | 7d | bar: WEEK 1 TH to WEEK 2 TH
Mockups | UX Designer & Front-end Developer | 4d | bar: WEEK 2 T to WEEK 2 TH
Design meeting | PM, UX, Front-end Dev with Stakeholders | 1d | bar: WEEK 2 F
Design adjustments | UX Designer & Front-end Developer | 2d | bar: WEEK 3 M
Development |  | 5d
Built Website | Front-end Developer | 5d | bar: WEEK 3 T to WEEK 4 M
Implementation |  | 4d
Usability testing and adjusting | UX Designer | 4d | bar: WEEK 3 F to WEEK 4 W
Testing and adjusting | Front-end Developer | 3d | bar: WEEK 4 T to WEEK 4 TH
Approval and Launching | Project Manager & Front-end Developer | 1d | bar: WEEK 4 F
Gannt Chart template made by studiobinder.com tweaked by Svanhild Sleire for Noroff school project 2019

## Month 1
Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 5 d
Finalize Script | owner | 2 d
Attachments | owner | 3 d
Financing | owner
PRE-PRODUCTION |  | x d
Casting | owner
Set Design | owner
Locations | owner
Costumes | owner
Hair | owner
Make-up | owner
PRODUCTION |  | x d
Rehearsals | owner
Principal Photography | owner
Second Unit | owner
POST-PRODUCTION |  | x d
Editing | owner
VFX | owner
Scoring | owner
Sound Editing | owner
Color Grading | owner
DISTRIBUTION |  | x d
Distribution Deals | owner
Marketing Push | owner
Press Tour | owner
Premieres | owner
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
#NAME? |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder